## WP2
INDICATOR | THRESHOLD | KPI Code | 1st Period | Total amount | 3rd Period
SMEs, startups, and mid-caps reached | 1500 | WP2-1 | 1400 | 1500
SMEs, startups, and mid-caps in SMART4ALL DIH | 100 | WP2-2 | 467 | 557
SMEs in SMART4ALL Consortium | 10 | WP2-3 | 10 | 10
Digital skills growth: organization of summer school | 4 | WP2-4 | 5 | 8
Digital skills growth: organization of technology training oriented open courses | 4 | WP2-5

## WP3
INDICATORS | THRESHOLD |  | KPI Code | 1st Period | Total amount | 3rd Period
Participation in pitching events for each PAE | 2 | 2 | WP3-1 | 11 | 2
-- Website hits | 25000 (4000+unique visitors) | 25000 | WP3-2.1 | 4164 | 27527
-- Social media followers | 1000+ | 1000 | WP3-2.2 | 938 | 2288
-- Project newsletters | 8 | 8 | WP3-2.3 | 1 | 5
-- Pillar specific newsletters | 4 for each thematic pillar | 4 | WP3-2.4 | 3 | 0
-- Newsletter subscribers | 1000+ | 1000 | WP3-2.5 | 380 | 684
-- Press release | 9 press release made at strategic moments of the project | 3 | WP3-2.6 |  | 7
-- Whitepapers | 2 | 2 | WP3-2.7
-- Distributed printed material | 3000 | 3000 | WP3-2.8 |  | 1000
-- Professional Videos | 10 SMART4ALL Teaser videos+ 30 (at least) for selected PAE success stories | 40 | WP3-2.9 |  | 14
-- Participation in Pitching Events | 1 per year | 4 | WP3-2.10 | 1 | 4
-- Webinars | 12 web-based | 12 | WP3-2.11 | 6 | 16
-- Participation in innovation Events | 1 per year | 4 | WP3-2.12 |  | 4
-- Participation in events organized by the EEN or H2020 NCP | 32 | 32 | WP3-2.13 |  | 5
-- Interaction with other SAE initiatives | 9 similar projects (5 unnning projects under the Call 2016 + other 4 approved under the Call 2019) | 9 | WP3-2.14 |  | 7

## WP4
INDICATORS | THRESHOLD | KPI Code | 1st Period | Total amount | 3rd Period
Business Coaching Sessions in each PAE | 3 | WP4-1 |  | 5
Private Investors reached into SMART4ALL activities through SMART4ALL MaaS service | 100 | WP4-2 |  | 100
Private Investors in SMART4ALL DIH | 20 | WP4-3 |  | 20
Representatives from Public Funding Sectors reached | 80 | WP4-4 |  | 80
Representatives from Public Funding Sectors in SMART4ALL DIH | 80 | WP4-5 |  | 80
Entrepreneurs reached | 30 | WP4-6 |  | 30
Entrepreneurs in SMART4ALL DIH | 10 | WP4-7 |  | 100
Organization of Business Development webinars | 4 | WP4-8 |  | 1
Organization of “How to write a Business Plan” workshops | 2 | WP4-9 |  | 2
Organization of “How to become an Entrepreneur” workshops | 2 | WP4-10 |  | 0

## WP5
INDICATORS | THRESHOLD | KPI Code | 1st Period | Total amount | 3rd Period
Agriculture number of artifacts | 30 | WP5-1 | 7 | 10
Transport number of artifacts | 20 | WP5-2 | 3 | 5
Environment number of artifacts | 40 | WP5-3 | 2 | 2
Anything number of artifacts | 40 | WP5-4 | 53 | 70
Number of users |  | WP5-5 | 772 | 772
Activity statistics: number of countries |  | WP5-6 | 54 | 54

## WP6
INDICATORS | THRESHOLD |  | KPI Code | 1st OC | 2nd OC | 3rd OC
SMEs, startups, and mid-caps participating in granted PAEs | 60% | 60% | WP6-1 | 68% | 64% | 73%
SMEs, startups, and mid-caps participating in granted PAEs from South and Eastern European countries | 40% | 40% | WP6-2 | 40% | 47% | 51%
Industrial beneficiaries participating in granted PAEs | 65% | 65% | WP6-3 | 75% | 79% | 73%
SMEs, start-ups, and mid-caps participation in Open Calls | 50% | 50% | WP6-4 | 64% | 60% | 75%
SMEs, startups, and mid-caps participating in granted PAEs from South and Eastern European countries | >50% | 50% | WP6-5 | 47% | 49% | 44%
Industrial partners participating in open calls | 60% | 60% | WP6-6 | 81% | 79% | 76%
Submitted applications against started applications. | Not defined | Not defined | WP6-7 | 45% | 36% | 53%
Participation of each Task Force. Environment, Transport, Anything and Agriculture | Not defined |  | WP6-8
Profile participants. Industrial SMEs / Slightly bigger, System integrator and Technology provider, University/Research/Academic | Not defined |  | WP6-9
INDICATORS |  |  | 1st KTE | 1st FTTE | 1st CTTE | 2nd KTE | 2nd FTTE | 2nd CTTE | 3rd KTE | 3rd FTTE | 3rd CTTE | 1st OC | 2nd OC | 3rd OC
SMEs, startups, and mid-caps participating in granted PAEs | 60% |  | 63% | 75% | 67% | 50% | 75% | 67% | 70.59% | 75% | - | 68.33% | 64% | 72.79%
SMEs, startups, and mid-caps participating in granted PAEs from South and Eastern European countries | 40% |  | 31% | 63% | 25% | 50% | 50% | 42% | 52.94% | 50% | - | 39.67% | 47.33% | 51.47%
Industrial beneficiaries participating in granted PAEs | 65% |  | 63% | 88% | 75% | 73% | 88% | 75% | 71% | 75% | - | 75.33% | 78.67% | 73%
SMEs, start-ups, and mid-caps participation in Open Calls | 50% |  | 62% | 62% | 67% | 50% | 63.33% | 66% | 72.73% | 78% | - | 63.67% | 59.78% | 75.36%
SMEs, startups, and mid-caps participating in open calls from South and Eastern European counties | 50% |  | 27% | 27% | 88% | 38% | 67.2% | 43% | 50% | 38% | - | 47.33% | 49.4% | 44%
Industrial partners participating in open calls | 60% |  | 73.87% | 88% | 82% | 78% | 82.67% | 76% | 73% | 78% | - | 81.29% | 78.89% | 75.5%
Submitted applications against started applications. | - |  | 12% | 40% | 35% | 26% | 41% | 42% | 55% | 51.3% | - | 29% | 36.33% | 53.15%
Participation of each Task Forces. Environment | - |  | 0% | 23.23% | 20.27% | 34.78% | 24.66% | 27.27% | 22.22% | 15% | - | 14.5% | 28.9% | 18.61% | Environment
Participation of each Task Forces. Transport | - |  | 17% | 10.1% | 16.22% | 4.348% | 20.55% | 23.64% | 13.89% | 24% | - | 14.44% | 16.18% | 18.94% | Transport
Participation of each Task Forces. Anything | - |  | 66% | 40.4% | 31.08% | 47.83% | 32.88% | 34.55% | 47.22% | 41% | - | 45.83% | 38.42% | 44.11% | Anything
Participation of each Task Forces. Agriculture | - |  | 17% | 26.26% | 32.43% | 13.04% | 21.92% | 14.55% | 16.67% | 20% | - | 25.23% | 16.5% | 18.33% | Agriculture
Profile participants. Industrial SMEs / Slightly bigger | - |  | 62% | 62% | 67% | 50% | 63.33% | 65% | 72.73% | 78% | - | 63.67% | 59.44% | 75.36% | SMEs
Profile participants. System integrator and Technology provider | - |  | 12% | 12% | 15% | 28% | 19.33% | 11% | 0% | 0% | - | 13% | 19.44% | 0% | Technology provider
Profile participants. University/Research/Academic | - |  | 26% | 26% | 18% | 22% | 16.67% | 24% | 27.27% | 22% | - | 23.33% | 20.89% | 24.64% | Academic
Total submitted applications |  |  | 12 | 99 | 85 | 24 | 75 | 61 | 36 | 79 | -
Total applications started |  |  | 97 | 247 | 245 | 92 | 182 | 145 | 65 | 154 | -
Eligible applications |  |  | 11 | 97 | 74 | 23 | 71 | 55 | 36 | 59 | -
Number of projects selected |  |  | 8 | 4 | 4 | 17 | 4 | 4 | 18 | 4 | -

## Task8.8
KPI | TARGET |  |  | 1st Period | Total amount | 3rd Period
Sensitive social groups are engaged in SMART4ALL | >50 people from sensitive social groups (SSG's) have been reached and engaged. | 50 | 1 |  | 18
SMART4ALL addresses the needs of sensitive social groups through low-energy computing powering CPS and IoT products and services. | 60% positive answers in respective questionnaires | 60% | 2 |  | 75%
Increase the number of services for people from sensitive social groups that utilize low energy computing powering CPS and IoT products and services | >10 funded PAEs | 10 | 3 |  | 6
PAEs for people from sensitive social groups | >10 | 10 | 4 |  | 17